## Overview
SUMMARY
Project Overview | Detailed Report of BUG affecting the functionality of the project with respect to user requirement.
Project Name | eHIE Web Portal
Product Description | Login and Sign-Up Page Manual Testing
Project Status | Project Type | Verification/Validation
Project Duration | Start Date | 2022-03-08 | End Date | 2022-09-23

## Report
PROJECT NAME : eHIE Web Portal |  |  |  |  | BUG SUMMARY |  | Level | User Impact |  | Business Impact |  | Status | Reviewed By
Module Name: BUG Report | [6 empty] | Critical | 80-100% |  | 80-100% |  | þ | Manager
Dependencies: Manual Test Case | [6 empty] | High | 70-80% |  | 70-80% |  | þ | Manager
Test Priority (Low/Mid/High/Highest): |  |  | High |  |  |  | Medium | 50-70% |  | 50-70% |  | þ | Manager
[7 empty] | Low | 20-50% |  | 20-50% |  | þ | Manager
BUG ID | Test Case ID | BUG Description | Steps to Find if Required | Founded Date | Reported By | Assigned To | Priority | Severity | Type | Reproducibility | Linked Issue | Status | Environment | Remarks | Attachment
#0001 | SW-244 | Impact of bug with respect to user requirement | Open the Login Page Look for page | 2022-03-04 | Trainee | Developer | 2 | Medium | UI/UX Bug | Everytime | SW-389 | To Do | Login Portal Page
#0002 | EG-567 | Impact of bug with respect to user requirement | Open the Login Page Enter Username and password Click Submit | 2022-03-01 | Tester Name | Developer | 4 | Lowest | Functional | Random | SW-302 | Resolve | Web Page
#0003 | SW-244 | Impact of bug with respect to user requirement | Open the Login Page Enter Username and password Click Submit | 2022-03-05 | Developer Name | Developer | 1 | Highest | Non-Functional | Everytime | SW-423 | Unresolve | Application
#0004 | EG-567 | Impact of bug with respect to user requirement | Open the Login Page Enter Username and password Click Submit | 2022-03-04 | Team Leader | Developer | 3 | Medium | Ad-hoc | Random | SW-412 | In-Progress | Web Page
#0005 | SW-312 | Impact of bug with respect to user requirement | Open the Login Page Enter Username and password Click Submit | 2022-03-04 | Project Manager | Developer | 1 | Highest | Design | Everytime | SW-380 | Resolve | Application

## Summary
PROJECT NAME : eHIE Web Portal |  |  |  |  | Resolved Bugs |  | 2 | Version | 1.9.0
Module Name: BUG Report Summary |  |  |  |  | Unresolved Bugs |  | 1 | Date | 2022-03-04
Dependencies: Report |  |  |  |  | Open Bug |  | 2
Test Priority (Low/Mid/High/Highest): |  |  | High |  | Total no of defects |  |  |  | 5
Sr No | Bug ID | Bug Description | Priority | Severity | Impact | Status
1 | #0050 | User is able to login with invalid password | 2 | Medium | High | Resolved
2 | #0077 | Multiple time start and close procedure app crashes | 4 | Lowest | Low | Unresolved
3 | #0253 | User is unable to end the procedure in acetic acid | 1 | Highest | High | Resolved
4 | #0347 | Captured image and preview image are different | 3 | Medium | Medium | In-Progress
5 | #0369 | User is unable to generate report after the procedure | 1 | Highest | High | Open